## Slide 1: Switch4Schools Roll Out Plan for educators
Week 1 Planning
Week 2 Awareness
Week 5 - 7 Build Routines
Week 8 + Embedded Practice
Week 3 Introduce Switch to Students
Week 4 Start check-ins
Continue to build knowledge of emotion language
Introduce appropriate switches based on previous week’s data
Refine routines for check-ins
Leverage available resources including ACTIVITIES and ENERGISERS
Introduce relevant emotion wheel
  refer POSTERS, and
  LESSONS mapped to Personal and Social capabilities
Introduce students to program
Choose avatars
  refer SELECTION SHEET
Admin:
  Set up school profile
  App deployed
  Parent consent/comms
Onboarding session
Receive login details
Bookmark APP
Refer GETTING STARTED GUIDE
Familiarise with functionality
Seek help if needed via:
  support@switch4schools.com.au
  HELP HUB
  Switch Champion/s
Continue to build knowledge of emotion language
Develop routines for check-ins
Explore available resources
Routines established
Resources used to reinforce class needs
Provide feedback via supplied survey